## IT Technical S
IT Tasks Tracking Sheet as of (3/09/2024)
# | Task/Project summary Description | Objectives | Severity/urgency | IT Department /Owner | Start date | Milestones/deliverables | Target date | Completion status % | Status as of 3/09/2024
1 | PCs replacement phase 2 (363 PCs non compliant with MS WIN 11) | Align with Windows 11 mandate for Endpoints Upgrade | 3 | IT Technical S | Q1 24 |  | Q1 2024 | 100% | Done
2 | Apply MS Jan 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-01-10 |  | 2024-01-11 | 100% | Done
3 | PCs replacement phase 2 (550 PCs non compliant with MS WIN 11) | Align with Windows 11 mandate for Endpoints Upgrade | 3 | IT Technical S | Q1 24 |  | Q3 2024 | 80% | In progrees
4 | Apply the following security patches: VMWare vcenter Version: 7.0.3 Build: 22837322 | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-01-08 |  | 2024-01-10 | 100% | Done
5 | Upgrade IT Service desk application, websphere and DB2 for security enhancement | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-01-08 |  | 2024-02-29 | 100% | Done
6 | Upgrade the following SQL 2014 servers Sigcap,DTS,Legal,DIDO, Asset track and Equitrack | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-01-28 |  | 2024-02-29 | 100% | Done
7 | Branches applications access rights periodic review (Round 1) | Performing applications access rights review (BI annual base) | 3 | IT Access rights | 2024-01-02 |  | 2024-02-19 | 100% | Done
8 | Apply MS Feb 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-02-18 |  | 2024-02-26 | 100% | Done
9 | Apply the following security patches: VMWare EXSI Version: 7.0 Build: 23307199 | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-03-10 |  | 2024-03-10 | 100% | Done
10 | Apply MS March 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-03-12 |  | 2024-03-14 | 100% | Done
11 | EY audit requirement |  |  | IT Access rights & IT Technical S |  |  |  | 100% | Done
12 | COSO requirement |  |  | IT Access rights & IT Technical S |  |  |  | 100% | Done
13 | IP phones replacement |  |  | IT Technical S |  |  |  | 100% | Done
14 | Vmware & Veeam licenses renewal |  |  | IT Technical S | 2024-01-28 |  | 2024-04-17 | 100% | Done
15 | Access rights Internal Audit mission |  |  | IT Access rights | 2023-11-19 |  | 2024-03-31 | 100% | Done Satisfactory
16 | Helpdesk Internal Audit mission |  |  | IT Technical S | 2023-12-19 |  | 2024-03-31 | 100% | Done Satisfactory
17 | Apply MS April 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-04-15 |  | 2024-04-17 | 100% | Done
18 | Distruction of HDDs of replaced PCs | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-04-18 |  | 2024-04-22 | 100% | Done
19 | Apply MS May 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-05-19 |  | 2024-05-21 | 100% | Done
20 | Departments applications access rights periodic review (Round 1) | Performing applications access rights review (BI annual base) | 3 | IT Access rights | 2024-01-02 |  | 2024-05-19 | 100% | Done
21 | Apply the following security patches: VMWare vcenter Version: 7.0.3 Build: 24026615 | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-06-25 |  | 2024-06-26 | 100% | Done
22 | Apply MS June 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-06-25 |  | 2024-06-26 | 100% | Done
23 | Apply MS July 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-07-17 |  | 2024-07-21 | 100% | Done
24 | Apply MS August 2024 security updates for IT-Technical S servers scope | IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 2 | IT Technical S | 2024-08-13 |  | 2024-08-20 | 100% | Done

## IT Techncial
IT Tasks Tracking Sheet as of 12/1/2025
# | Task/Project summary Description | Objectives | Severity/urgency | IT Department /Owner | Start date DD/MM/YYYY | Milestones/deliverables | Target date DD/MM/YYYY | Adjust Target date DD/MM/YYYY | Completion status % | Status as of 3/11/2024
1 | Intercom -Instant payment Network (IPN) PSP-pre authorized | Prioritize regulatory requirements, CBE | 1 | Technical-L | 2023-06-06 | N/A | 2024-06-01 | 13/1/2025 | 90% | Go live by Monday 13/1/2025
2 | FAWRY - Wallet Unified Built 3 | N/A | 1 | Technical-L | 2023-03-08 | FIX issues from Round 1 | 2023-03-11 | 31/1/2025 | 85% | Remaining From Fawry Side : 1- in progess - Pen Test Report 2- Provide go live plan (Pilot) . The bank needs to send request to CBE for approval having 1- Clean grey pen. Test report. 2- Authounticated vulnerability scan.
3 | Fawry - ربط المحفظة الاليكترونية لحساب عملاء اخرين وحسابات داخلية دون تحقق | Prioritize regulatory requirements, CBE | 1 | Technical-L | 23/8/2023 | waiting Vendor feedback | 23/9/2023 | 31/1/2025 | 50% | Apply the Account Validation during (Account adding / Cards adding ) will be considering and mitigate within Unified build “ Wallet3 “
4 | AIS - OS OTP Upgrade | Enhancement Implementing Digital services innovation (ongoing) | 1 | Technical-L | 2023-10-05 | N/A | 31/12/2023 | 31/1/2025 | 50% | intercom deployment in progress
5 | Intercom - IPN Modification CR Bulliten# 11 /12 (Issuer & PSP Preauthorized) | Prioritize regulatory requirements, CBE | 1 | Technical-L | 28/1/2024 | finalize PSP UAT | 2024-01-06 | 2025-12-01 | 95% | go live Sunday 12/1/2025
6 | e-Finance integration (New web services on App Connect to allow any interface to integrate with e-Finance " TAX , Customs , Payment" ) | N/A | 1 | Technical-L | 15/4/2024 | N/A | 15/5/2024 | 31/1/2025 | 45% | 1- Web services development was done from our Dept. Side. 2-simple test in progress with e-Finance 3-Issac are building the screens for E-finance services
7 | Fawry Report server : Business reports issues | Prioritize regulatory requirements, CBE | 1 | Technical-L | 2023-03-08 | to upgrade Fawry reporting production server to WIN 2019 | 2023-03-12 | 31/1/2025 | 90% | Balance report issues solved - waiting Go live plan with Wallet3 to go live.
8 | AS/400 missing licensees not listed | N/A |  | Technical-L | 2022-12-01 | N/A |  |  |  | waiting IBM/ISYS to provide the license.
9 | New Flash storage sizing and planning | N/A | 1 | Technical-L | 2023-07-12 | N/A | 20/6/2024 | 31/1/2025 | 95% | provided vendor Doc "SAVEGuard Activities) in studing with our team. waiting vendor reply for some inquires next week
10 | Tape library & encryption tools |  |  | Technical-L |  | N/A |  | 30/12/2024 | 40% | POC was hold with CommVault (Isky) - vendor failed to apply UB Pre-Requisities
11 | two POs on hold “Intercom” 2018 &2020 " RPG to Java " |  |  | Technical-L |  | N/A |  |  |  | Memo with top management
12 | Intercom - IPN CR Bulliten# 13/14 | N/A |  | Technical-L |  | N/A | 30/6/2024 | 30/12/2024 | 50% | Go live Sunday 12/1/2025
13 | Card Tokenization | N/A |  | Technical-L |  | N/A |  | 30/12/2024 | 10% | waiting intercom proposal
14 | Corporate PSP
15 | E-Remittance PSP

## IT-Admin
IT Tasks Tracking Sheet
# | Task/Project summary Description | Objectives | Severity/urgency | IT Department /Owner | Start date DD/MM/YYYY | Milestones/deliverables | Target date DD/MM/YYYY | Completion status % | Status as of 03-09-2024
1 | Microsoft Unified Support Renewal |  | 1 | IT-Admin | 2023-12-20 | Contract signed by UB & MS | 2024-02-15 | 100% | Finished
2 | Patch management system Tender | Aligned with CBE Cyber security framework, IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 1 | IT-Admin | 2023-11-01 |  | 2024-09-30 | 90% | Working now with ManageEngine PoC and waiting budgetary offer to proceed with Tender
3 | PAM onboarding on IT-Admin scope |  | 1 | IT-Admin | 2023-10-01 | user ayman-mgmt has been onboarded | 2024-08-31 | 100% | Finished
4 | TUB PCI-DSS Renewal | Renewal with ISO team the PCI /DSS certifications | 2 | IT-Admin |  |  |  | 100% | pre- requisites has been sent
5 | PCI Internal VA Mitigation | Renewal with ISO team the PCI /DSS certifications | 2 | IT-Admin |  |  | 2024-02-29 | 100% | Finished
6 | Deploying MS April-2024 |  | 2 | IT-Admin | 2024-03-13 |  | 2024-04-30 | 90% | Deployed expecpt non-updating Servers (OPICS,Xmark,WF)
7 | IT-Admin Training Plan | IT Staff Training | 3 | IT-Admin | 2024-01-01 |  | 2024-12-31 |  | Working on other team members
8 | Finance Deprt. File Server | Expanding infrastructure high availability in alignment with the Business needs | 2 | IT-Admin | 2024-01-01 | GC Fileserver Completed | 2024-01-03 | 100% | Finished
9 | SMG Mail Gateway License Renewal |  | 1 | IT-Admin | 2023-12-20 | PO Has been sent | 2024-02-01 | 100% | Finished
10 | Upgrade SQL Server 2014 (EOF) |  | 3 | IT-Admin | 2024-01-10 | All Scope have been upgraded | 2024-06-30 | 100% | Finished
11 | Email Public Certificate Renewal |  | 3 | IT-Admin | 2024-02-15 |  | 2024-04-01 | 100% | Finished
12 | Installing CU14 "Cumulative Update" on Exchange Server 2016 and enabling Extended Protection |  | 1 | IT-Admin | 2024-02-15 |  | 2024-02-19 | 100% | Finished
13 | DLP Endpoint Server Disk space utilization fix |  | 1 | IT-Admin | 2024-02-15 | Move new spcace to C | 2024-02-29 | 100% | Finished
14 | Syamnec Complete Secure Licenses Renewal |  | 3 | IT-Admin | 2024-02-27 |  | 2024-06-01 | 100% | Finished
15 | Workstation vulnerabilities Scan March-2024 |  | 2 | IT-Admin | 2024-04-07 |  | 2024-04-30 | 100% | Finished
16 | Deploying MS May-2024 |  | 2 | IT-Admin | 2024-05-14 |  | 2024-05-30 | 80% | Deployed expecpt non-updating Servers (OPICS,Xmark,WF)
17 | MS Sahrepoint Update |  | 3 | IT-Admin | 2024-07-01 |  | 2024-09-30 | 35% | in progress
18 | Deploying MS June-2024 |  | 2 | IT-Admin | 2024-05-14 |  | 2024-05-30 | 80% | Deployed on IT-Admin scope and following up with other teams (IT-App,Oper)
19 | Data calssification Solution PoC | Aligned with CBE Cyber security framework | 2 | IT-Admin | 2024-06-27 |  | 2024-10-01 | 20% | Preparing PoC with DECE Vendor
20 | Deploying MS July-2024 |  | 2 | IT-Admin | 2024-07-09 |  | 2024-07-30 | 90% | Deployed expecpt non-updating Servers (OPICS,Xmark,WF)
21 | Health check |  | 3 | IT-Admin | 2024-08-01 |  | 2024-08-30 | 50% | SCCM,Exchange and AD in progress
22 | Deploying MS Aug-2024 |  | 2 | IT-Admin | 2024-08-14 |  | 2024-08-30 | 85% | Deployed on IT-Admin scope and following up with other teams (IT-App,Oper)
23 | Updates EDR connection with all endpoints |  | 3 | IT-Admin | 2024-08-15 |  | 2024-09-30 | 100% | Solved
24 | DR Domain Controller fix OS crash |  | 2 | IT-Admin | 2024-08-18 |  | 2024-09-15 | 10% | OS Broken again and Nile.com is working to permeant fix
25 | Google Chrome Security Update - 22 August 2024 |  | 2 | IT-Admin | 2024-08-22 |  | 2024-08-23 | 100% | The needed update has been deployed
26 | Microsoft Edge Security Update - 25 August 2024 |  | 2 | IT-Admin | 2024-08-25 |  | 2024-08-26 | 100% | The needed update has been deployed
27 | Google Chrome Security Update - 29 August 2024 |  | 2 | IT-Admin | 2024-08-29 |  | 2024-08-30 | 100% | The needed update has been deployed
28 | Google Chrome Security Update - 03 September 2024 |  | 2 | IT-Admin | 2024-09-03 |  | 2024-09-04 | 100% | The needed update has been deployed

## IT-Network
IT Tasks Tracking Sheet
# | Task/Project summary Description | Objectives | Severity/urgency | IT Department /Owner | Start date DD/MM/YYYY | Milestones/deliverables | Target date DD/MM/YYYY | Completion status % | Status as of 03-09-2024
1 | Replace Noor Lines (I-Score,MCDR) | Expanding infrastructure high availability in alignment with the Business needs | 2 | IT-Network |  | VF Failed, new PO for Etisalat has been issued | 2024-06-01 | 100% | Both lines have been replaced
2 | Firemon Firewalls policy\StealthBit Password black list POC | Aligned with CBE Cyber security framework,IT infrastructure systems / applications security reviews ((Implement Patch management solution) | 1 | IT-Network |  |  | 2024-09-30 | 50% | Hold By CEO,Negetiong with Vendors to get same cost to refer back to CEO
3 | DC Messaha Relocation | Data Center Relocation actions | 1 | IT-Network | 2022-01-01 | Intital Offer redived and ISPs alignments |  | 10% | Hold
4 | MobileIron MDM User Transition | Aligned with CBE Cyber security framework | 1 | IT-Network | 2023-10-01 | All users are working on MDM except Top-Management | 2024-09-30 | 95% | Pending 17 Users wait CIO Instruction
5 | TUB PCI-DSS Renewal | Renewal with ISO team the PCI /DSS certifications | 2 | IT-Network | 2023-10-01 |  |  | 100% | Final Audit Phase Finished
6 | New admin Capital Building MW | IT Infrastructure Requirements for UB New Building located at New Capital | 2 | IT-Network | 2024-03-31 | Microwave is UP on 31-03-2024 | 2024-03-31 | 100% | Finished
7 | New admin Capital Building Fiber | IT Infrastructure Requirements for UB New Building located at New Capital | 2 | IT-Network | 2024-03-31 | Waiting Building readiness (Power, IT Room) | N/A | 50% | Waiting Engineering Dept. to finidsh contract with ACUD to install ONU device and purchasing the devices
8 | New admin Capital Building Active Component Tender | IT Infrastructure Requirements for UB New Building located at New Capital | 2 | IT-Network | 202-08-01 | Tender is finished and got the best price and add-ons conformaion from Cisco | 2024-07-31 | 90% | Waiting EXCOM approval to issue the PO
9 | Call Center Enhancement "Integrate Sibel CRM With Finesse" | Enhancement Implementing Digital services innovation (ongoing) | 2 | IT-Network | 2023-09-01 | Test and UAT has been signed | 2023-11-30 | 100% | Finished
10 | NDR POC (Dark Trace\Fedelis\Vectra) | Aligned with CBE Cyber security framework | 1 | IT-Network | 2022-10-20 | Dark Trace & Fedelis POC completed and Vectra started 17-01-2024 | 2024-12-31 | 100% | Memo for Tender has been presented to CIO
11 | Call Billing System Upgrade | Enhancement Implementing Digital services innovation (ongoing) | 2 | IT-Network | 2023-12-28 | Finshed with UAT signed | 2024-03-31 | 100% | Finished
12 | Cisco UCS HQ Servers Replacement Tender | Assess enhancing Virtualization/Cloud (Replace HQ Collaboration Cisco UCS Servers, Cisco Hyper Flex Test clusters) | 1 | IT-Network | 2023-10-01 |  | 2024-09-30 | 40% | Waiting final offers from Cisco Partners.
13 | Replaceing Cisco IP-Phones across all bank for model 7912 | Enhancement Implementing Digital services innovation (ongoing) | 2 | IT-Network |  | All Branches finished | 2024-03-31 | 100% | Finished
14 | PaloAlto DNS Security POC | Aligned with CBE Cyber security framework | 1 | IT-Network |  | DNS is runniing on DR FW | 2024-06-30 | 100% | POC Finished
15 | IT-Network Training Plan | IT Staff Training | 3 | IT-Network |  | Islam Khattab gained COBIT Certificate | 2024-12-31 | 25% | Working on other team members
16 | Cisco Router HW EOS Repalcment |  | 2 | IT-Network |  | All HWs Replaced | 2024-03-31 | 100% | Finished
17 | Apply Fortinet Fortigate NGFW Security Updates to fix several vulnerabilities |  | 1 | IT-Network | 09-02-2024 | Upgrade Done | 09-02-2024 | 100% | Finished
18 | PaloAlto PAN-OS Upgrade |  | 2 | IT-Network | 18-02-2024 | Upgrade Done | 2024-02-23 | 100% | Finished
19 | Mobile Mail MDM Public Cert. Renewal |  | 2 | IT-Network | 18-02-2024 |  | 2024-02-19 | 100% | Finished
20 | Deploying MS Feb-2024 |  | 2 | IT-Network | 18-02-2024 |  | 2024-02-22 | 100% | Finished
21 | Emergency Downtime for Vodafone HQ Microwave Line |  | 1 | IT-Network | 2024-02-20 |  | 2024-02-21 | 100% | Finished
22 | Upgrade Symantec SMG messaging gateway |  | 2 | IT-Network | 16-02-2024 | Upgrade Done | 2024-02-29 | 100% | Finished
23 | Deploying MS March-2024 |  | 2 | IT-Network | 13-03-2024 |  | 2024-03-31 | 100% | Finished
24 | Replace defected Visa & MC Cisco FTD “Fire Power Threat Defense” NGFW/NGIPS |  | 1 | IT-Network | 01-04-2024 |  | 2024-04-01 | 100% | Finished
25 | Deploying MS April-2024 |  | 2 | IT-Network | 07-04-2024 |  | 2024-04-30 | 100% | Finished
26 | Major Upgrade for Cisco ISE OS |  | 2 | IT-Network | 09-04-2024 | Upgrade Done | 2024-04-13 | 100% | Finished
27 | Upgrade Cisco Nexus Core switch OS |  | 2 | IT-Network | 12-04-2024 | DR Done, HQ Done | 2024-04-25 | 100% | Finished
28 | HQ Dokki Building Etisalat MW |  | 2 | IT-Network | 2024-03-14 | Microwave is UP on 15-05-2024 | 2024-05-16 | 100% | Finished
29 | DR Ocotber Building Etisalat MW |  | 2 | IT-Network | 2024-04-01 | Done | 2024-07-30 | 100% | In Progress (Engineering dept impleneting new ladder)
30 | Cisco Umbrella DNS Security | Aligned with CBE Cyber security framework | 1 | IT-Network | 2024-01-01 | Implemention Done for HQ/DR/Laptops | 2024-07-01 | 100% | Finished
31 | Apply Fortinet Fortigate NGFW Security Updates to fix several vulnerabilities |  | 1 | IT-Network | 10-07-2024 | Upgrade Done | 19-07-2024 | 100% | Finished
32 | Apply Ivanti MDM OS Upgrade to fix several vulnerabilities |  | 1 | IT-Network | 22-07-2024 | Upgrade Done | 24-07-2024 | 100% | Finished
33 | DR Data Center Cabling Arrangement |  | 3 | IT-Network | 21-07-2024 |  | 30-08-2024 | 70% | Pening 4 Racks and 9 Standalone servers
34 | Deploying MS Aug-2024 |  | 2 | IT-Network | 2024-08-14 | Upates Done | 2024-08-30 | 100% | Finished
35 | F5 Big-IP OS Upgrade |  | 2 | IT-Network | 2024-08-18 | Upgrade Done | 2024-08-22 | 100% | Finished
36 | Apply Security Patch on Cisco Nexus Core Switch to mitigate NX-OS Software Python Sandbox Escape Vulnerabilities |  | 2 | IT-Network | 2024-08-31 |  | 2024-09-06 | 30% | Working on DR first then HQ
37 | Users Call Manager CUCM upgrade |  | 2 | IT-Network | 2024-08-31 |  | 2024-09-30 | 30% | New Caluster has been created to café/Security